## 403
Multi-Axis Cobot for Factory Automation Gantt Chart
Week of:
| Titles | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | Date Completed
Key: | Defining Project Scope (8/27) | [15 empty] | 2024-08-27
Black - ALL | Subsystem Division / Brainstorming (9/3) | [12 empty] | Not Started |  |  | 2024-09-03
Green - Adrian Guzman | Creating a Budget Parts List (9/10) | [12 empty] | In Progress |  |  | 2024-09-12
Purple - Jaishil Shah | Subsystem Software Initialization (9/10/24) | [12 empty] | Completed |  |  | 2024-09-17
Blue - Emily Hamsa | CONOPS Report (9/15) | [12 empty] | Behind Sch. |  |  | 2024-09-12
Red - Ethan Woods | Creating a (TI) Parts List (9/17) | [15 empty] | 2024-09-17
| Swift Compatability (9/17) | [15 empty] | 2024-09-17
| Motor Selection Finalization (9/20) | [15 empty] | 2024-10-08
| Complete Subsystem Introduction Project (9/24) | [15 empty] | 2024-09-24
| Subsystem Introduction Project (Emily) (9/27) | [15 empty] | 2024-09-30
| Project Selection Presentation (9/23) | [15 empty] | 2024-09-23
| FSR, IDC, Milestones and Validation plan (9/26) | [15 empty] | 2024-06-26
| Parts Selection Finalization and Battery Sizing (9/27) | [15 empty] | 2024-10-13
| Competed PMS PCB Design and Ordering (10/11) | [15 empty] | 2024-10-23
| Mid-Term Presentation (10/14) | [15 empty] | 2024-10-14
| PCB Design with MCU (10/18) | [15 empty] | 2024-10-22
| Order PCB Board & Components (10/18) | [15 empty] | 2024-10-22
| Motor/Motor Driver Testing with EVM Board (10/18) | [15 empty] | 2024-10-08
| Apple Developer Status / Flutterflow Crash Course (10/20) | [15 empty] | 2024-10-15
| Subsystem Introduction Project (Jaishil) (10/20) | [15 empty] | 2024-10-17
| Subsystem Introduction Project (Ethan) (10/20) | [15 empty] | 2024-10-15
| Software on eval board (LED Blink & Motor Spin) (10/29) | [15 empty] | 2024-10-25
| Bluetooth Integration & ESP-32 Communication (11/5) | [15 empty] | 2024-11-05
| PCB Assembly and Soldering (11/08) | [15 empty] | 2024-11-08
| PCB Testing and Debugging (11/22) | [15 empty] | 2024-11-25
| PCB Assembly & Soldering (11/4) | [15 empty] | 2024-11-05
| PCB Design and Ordering (11/4) | [15 empty] | 2024-11-01
| ESP-32 PCB Design and Ordering (11/5) | [15 empty] | 2024-11-05
| Final Presentation (11/11) | [15 empty] | 2024-11-11
| Verify signals on PCB board | [15 empty] | 2024-11-08
| JTAG debugger connection to MCU | [15 empty] | 2024-11-12
| LED Blink/Stepper Motor on PCB | [15 empty] | 2024-11-19
| Soldered and Functional ESP-32 (11/22) | [15 empty] | 2024-11-22
| Solder Phase A, Phase B, and Phase C Boards (11/19) | [15 empty] | 2024-11-12
| PWM Signal Generation & ESP-32 Communication | [15 empty] | 2024-11-24
| Generate Phase Signals on Different Boards (11/25) | [15 empty] | 2024-11-18
| Subsystem Demonstration (Jaishil) (11/26) | [15 empty] | 2024-11-26
| Subsystem Demonstration (Ethan) (11/26) | [15 empty] | 2024-11-26
| Subsystem Demonstration (Emily) (11/26) | [15 empty] | 2024-11-26
| Subsystem Demonstration (Adrian) (11/26) | [15 empty] | 2024-11-26
| Final Report (12/5) | [15 empty] | 2024-12-05

## 404
Multi-Axis Cobot for Factory Automation Gantt Chart
Week of:
| Titles | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | Date Completed
Key: | Bi-Weekly Status Update #1 (a) (1/15)
Black - ALL | Redesign PCB to include new rails and power plains (1/17) | [12 empty] | Not Started
Green - Adrian Guzman | Place PCB and components order(1/17) | [12 empty] | In Progress
Purple - Jaishil Shah | Redesign Schematics and PCB Design (1/17) | [12 empty] | Completed
Blue - Emily Hamsa | Finalize design of new PCB (1/17) | [12 empty] | Behind Sch.
Red - Ethan Woods | Order PCB and components (1/17)
Order PCB and Components (1/20)
Finalize App Design (1/24)
Assemble PCB (1/29)
Assemble new PCB (1/29)
Assemble and Solder Final PCB (1/31)
Work on Physical Design Modifications (1/31)
Wirelessly communcate to cobot motors (2/6)
Integrate Bluetooth functionality with other subsystems (2/3)
Validate functionality of PCB & Software (2/3)
Bi-Weekly Status Update #2 (a) (2/3)
Begin Integration (2/3)
Test and Validate PCB (2/5)
Develop software for 4-axis Servo Movement (2/10)
Develop software for wireless input to MCU (2/10)
Test and Validate PCB (2/7)
Prepared physical design for integration (2/10)
Begin Integration with team subsystems (2/10)
Begin Integration with team subsystems (2/10)
Begin Integraion with MCU Subsystem (2/10)
BLDC motor spinning through CCS software (2/19)
Solder second MCU board (2/20)
Finalize motor softwares / fix bugs (2/24)
Integrated physical design (2/24)
Bi-Weekly Status Update #3 (a) (2/17)
Identify and Fix Issues during integration (3/7)
Bi-Weekly Status Update #4 (a) (3/3)
Fix issues encountered during integration (3/31)
Bi-Weekly Status Update #5 (a) (3/24)
Final Design Presentation (4/7)
Final Demo (4/21)
Final Report Due (4/28)